## APQP Tracker
# | Phase | Deliverable | Output / Artifact (example) | PPAP Req'd | Owner | Due Date | Status | % Complete | Comments / Notes
1 | Phase 1 - Planning | Product design requirements | VOC summary, engineering spec document, applicable standards/regulatory list, design intent statement | N |  |  | Not Started | 0%
2 | Phase 1 - Planning | Project targets (safety, quality/manufacturability, service life, reliability, durability, maintainability, schedule, cost) | Quantified target sheet (PPM target, warranty target, DFMEA severity thresholds, target cost/piece, program timing milestones) - CFT signed off | N |  |  | Not Started | 0%
3 | Phase 1 - Planning | Preliminary listing of Critical Items (CIs) and Key Characteristics (KCs) | Draft CI register and KC matrix linked to customer print/spec with rationale | N |  |  | Not Started | 0%
4 | Phase 1 - Planning | Preliminary BOM | Multi-level BOM (make/buy flagged), draft part numbering, engineering revision level noted | N |  |  | Not Started | 0%
5 | Phase 1 - Planning | Preliminary process flow diagram | High-level box diagram (receiving to shipping) showing major process steps | N |  |  | Not Started | 0%
6 | Phase 1 - Planning | SOW review | SOW gap analysis / compliance checklist vs. customer contract, action item log | N |  |  | Not Started | 0%
7 | Phase 1 - Planning | Preliminary sourcing plan | Make/buy decision matrix, candidate supplier list, sourcing timing plan | N |  |  | Not Started | 0%
8 | Phase 1 - Planning | Project plan | APQP timing chart (Gantt), RACI/team roster, milestone/gate schedule, program risk log | N |  |  | Not Started | 0%
9 | Phase 2 - Product Design & Development | Design risk analysis | DFMEA (initial), design review checklist, risk ranking (RPN/AP) | Y |  |  | Not Started | 0%
10 | Phase 2 - Product Design & Development | Design records and BOM (addressing DFMEA findings) | Released/updated drawings, 3D models, engineering BOM revised to close DFMEA actions | Y |  |  | Not Started | 0%
11 | Phase 2 - Product Design & Development | Special requirements, product KCs and CIs listings | Finalized special characteristics matrix (customer symbols), CI/KC list with control method flagged | N |  |  | Not Started | 0%
12 | Phase 2 - Product Design & Development | Preliminary risk analysis of sourcing plan | Supplier risk assessment (capability, capacity, financial, geographic), mitigation plan | N |  |  | Not Started | 0%
13 | Phase 2 - Product Design & Development | Packaging specification | Returnable/expendable packaging spec, packaging drawing, labeling requirements draft | N |  |  | Not Started | 0%
14 | Phase 2 - Product Design & Development | Design review report | Formal DR meeting minutes, action item log with owners/due dates, sign-off sheet | N |  |  | Not Started | 0%
15 | Phase 2 - Product Design & Development | Development product build plan | Prototype/proto-build control plan, build schedule, resource/tooling requirements | N |  |  | Not Started | 0%
16 | Phase 2 - Product Design & Development | Design verification and validation plans, and associated results | DVP&R with test results and pass/fail status | N |  |  | Not Started | 0%
17 | Phase 2 - Product Design & Development | Feasibility assessment | Manufacturing feasibility commitment sign-off (mfg, quality, purchasing, tooling), feasibility risk log | N |  |  | Not Started | 0%
18 | Phase 3 - Process Design & Development | Process flow diagram | Detailed station-by-station flow diagram matching PFMEA/Control Plan numbering | Y |  |  | Not Started | 0%
19 | Phase 3 - Process Design & Development | Floor plan layout | Facility/line layout drawing showing material flow, WIP, inspection points, ergonomics | N |  |  | Not Started | 0%
20 | Phase 3 - Process Design & Development | Production preparation plan | Run-at-rate readiness checklist, pre-launch timing plan | N |  |  | Not Started | 0%
21 | Phase 3 - Process Design & Development | Operator staffing and training plan (HR) | Skills matrix, training plan/schedule, staffing headcount plan by shift | N |  |  | Not Started | 0%
22 | Phase 3 - Process Design & Development | PFMEA | Process FMEA linked to DFMEA/process flow, RPN/AP ranking, action plan | Y |  |  | Not Started | 0%
23 | Phase 3 - Process Design & Development | Process KCs | Process characteristic list mapped to product KCs, control method identified | N |  |  | Not Started | 0%
24 | Phase 3 - Process Design & Development | Control plan | Prototype/Pre-launch Control Plan (inputs, spec, method, sample size/freq, reaction plan) | Y |  |  | Not Started | 0%
25 | Phase 3 - Process Design & Development | Preliminary capacity assessment | Capacity study (theoretical vs. demonstrated), OEE assumptions, bottleneck analysis | N |  |  | Not Started | 0%
26 | Phase 3 - Process Design & Development | Work station documentation | Standard Work Instructions (SWI), visual aids, one-point lessons | N |  |  | Not Started | 0%
27 | Phase 3 - Process Design & Development | Measurement Systems Analysis (MSA) Plan | Gage list, MSA study schedule, gage R&R plan per characteristic | N |  |  | Not Started | 0%
28 | Phase 3 - Process Design & Development | Supply Chain Risk Management Plan | Sub-tier supplier risk register, contingency/dual-sourcing plan | N |  |  | Not Started | 0%
29 | Phase 3 - Process Design & Development | Material handling, packaging, labelling, and part marking approvals | Approved packaging trial report, label/barcode approval, part marking verification | Y |  |  | Not Started | 0%
30 | Phase 3 - Process Design & Development | Production Readiness Review (PRR) results | PRR scorecard, open issues list, go/no-go decision record | N |  |  | Not Started | 0%
31 | Phase 4 - Product and Process Validation | Product from production process run(s) | Run-at-rate/significant production run report (parts built at rate, tooling/process at intended state) | N |  |  | Not Started | 0%
32 | Phase 4 - Product and Process Validation | MSA | Gage R&R results (%GRR, ndc), attribute agreement analysis, sign-off | Y |  |  | Not Started | 0%
33 | Phase 4 - Product and Process Validation | Initial process capability studies | Cpk/Ppk study report per KC, capability summary sheet | Y |  |  | Not Started | 0%
34 | Phase 4 - Product and Process Validation | Control plan | Production Control Plan (finalized, post run-at-rate) | Y |  |  | Not Started | 0%
35 | Phase 4 - Product and Process Validation | Capacity verification | Actual demonstrated capacity report vs. customer demand (parts/hr, OEE) | N |  |  | Not Started | 0%
36 | Phase 4 - Product and Process Validation | Product validation results | Functional/performance test report against DVP&R at production intent | N |  |  | Not Started | 0%
37 | Phase 4 - Product and Process Validation | First Article Inspection Report (FAIR) | AS9102 or equivalent FAIR, ballooned drawing, characteristic accountability | Y |  |  | Not Started | 0%
38 | Phase 4 - Product and Process Validation | PPAP file and approval form | Full PPAP package (elements 1-18 per AIAG), PSW signed by customer | Y |  |  | Not Started | 0%
39 | Phase 4 - Product and Process Validation | Customer specific requirements | CSR compliance checklist/matrix, evidence file per customer portal requirements | Y |  |  | Not Started | 0%
40 | Phase 5 - Serial Production and Feedback | Quality indices (CpK, PPM, rejection rates) | SPC dashboard, monthly quality scorecard, trend charts | N |  |  | Not Started | 0%
41 | Phase 5 - Serial Production and Feedback | Key Performance Indicators (KPIs) | KPI dashboard (safety, quality, delivery, cost) with targets vs. actuals | N |  |  | Not Started | 0%
42 | Phase 5 - Serial Production and Feedback | Evidence that project targets have been met | Phase 1 target closure report/matrix (traceability from targets to actual results) | N |  |  | Not Started | 0%
43 | Phase 5 - Serial Production and Feedback | On-time Delivery (OTD) and capacity KPIs | OTD trend report, capacity utilization report | N |  |  | Not Started | 0%
44 | Phase 5 - Serial Production and Feedback | OTD and capacity improvement plan | Corrective action plan with milestones for any red KPIs | N |  |  | Not Started | 0%
45 | Phase 5 - Serial Production and Feedback | Project closure recommendations | Program closure report, open issue disposition, customer sign-off | N |  |  | Not Started | 0%
46 | Phase 5 - Serial Production and Feedback | Continuous improvement actions | Kaizen/CI action log, cost/quality improvement tracker | N |  |  | Not Started | 0%
47 | Phase 5 - Serial Production and Feedback | Lessons learned | Lessons learned register (technical, process, program management) | N |  |  | Not Started | 0%
48 | Phase 5 - Serial Production and Feedback | Updated design risk analysis, PFMEA, and control plans | Revision-controlled living documents updated per field/warranty data, ECNs, or CI actions | N |  |  | Not Started | 0%

## Summary Dashboard
APQP Program Status Dashboard
Auto-calculated from APQP Tracker sheet — update owner/due date/status there.
Status | Count | Phase | Total Items | Complete | % Complete
Not Started | 48 | Phase 1 - Planning | 8 | 0 | 0%
In Progress | 0 | Phase 2 - Product Design & Development | 9 | 0 | 0%
Complete | 0 | Phase 3 - Process Design & Development | 13 | 0 | 0%
At Risk | 0 | Phase 4 - Product and Process Validation | 9 | 0 | 0%
Blocked | 0 | Phase 5 - Serial Production and Feedback | 9 | 0 | 0%
N/A | 0
Total Deliverables | 48
PPAP-Required Elements
Total PPAP items | 12
PPAP items complete | 0